## Introduction
Kelverion Test Plan Template
As we all know, plans can be as simple as a checklist or as complicated as a project plan with multiple people, phases, and levels of implementation. The same can be said for a Test Plan. Our Professional Services team at Kelverion has created a Test Plan Template you can download and use when it comes to testing your IT automation processes. So, we thought it would be beneficial if we explained most of the key things we have tried to incorporate and how they can be customized by you for your specific scenario. Let’s start by explaining what each part is designed to accomplish. Each tab of the template has a specific purpose. There are four (4) tabs: General – this is where you document the higher-level things involved with your testing such as the name of your company, the name of the project or task you are testing, the people involved with the testing process, dates you are starting and ending your testing process, and an overall status of each category of testing. Test Activity Control Log – this is where you document a little more detail about the success, completion, and/or results of your testing for each category. Test Plan Detail – this is where you document the individual steps necessary to be tested and whether they completed successfully. Glossary – this is where you document every tab, title, or item that is expected to be filled out on the Test Plan.

## General
Company Name
Project
Test Team Lead
Test Team Members
Test Start Date
Test End Date
URL
Browser
Test Summary | Overall Status (Red = Failed, Amber = Incomplete, Green = Passed)
Confirm Pre-requisites
Check Imported runbooks
Check PDS configuration / data baseline
Confirm Items are created/updated/assigned
Updated/Resolved Tickets
Other

## Test Activity Control Log
Test Summary | Success | Completed By | Date | Result Details (upon failure) | Remedial Actions (upon failure)
Confirm Pre-requisites
Check Imported runbooks
Check PDS configuration / data baseline
Confirm Items are created/updated/assigned
Updated/Resolved Tickets
Other

## Test Plan Detail
Category | Task | Pre-Condition | Step # | Step Description | Expected Result | Actual Result | Pass (True/False) | Defect # | Comments/Clarifications
Confirm prerequisites | Check Integrations are installed and functioning | None | 1-1 | Confirm IP for SQL Server is registered in deployment manager | IP Is registered
Confirm prerequisites | Check Integrations are installed and functioning | None | 1-2 | Check each Server to confirm IP for SQL Server is deployed | IP is deployed
Confirm prerequisites | Check Integrations are installed and functioning | None | 1-3 | Confirm IP Configuration for PDS_LIVE database exists | Connection exists
Confirm prerequisites | Check Integrations are installed and functioning | None | 1-4 | Check Connection for PDS_Live Database | Connection is successful during design time and runtime
Confirm prerequisites | Check Integrations are installed and functioning | None | 1-5 | Confirm IP for Service Desk is registered in deployment manager | IP Is registered
Confirm prerequisites | Check Integrations are installed and functioning | None | 1-6 | Check each Server to confirm IP for Service Desk is deployed | IP is deployed
Confirm prerequisites | Check Integrations are installed and functioning | None | 1-7 | Confirm IP configuration for Service Desk exists | Connection exists
Confirm prerequisites | Check Integrations are installed and functioning | None | 1-8 | Check Connection to Service Desk | Connection is successful during design time and runtime
Check Imported runbooks | Verify that in-scope runbooks are imported into the new instance | SCORCH_01 checks completed | 2-1 | Check that the runbook 10.1 is imported and is executing (Path to runbook 10.1)
Check Imported runbooks | Verify that in-scope runbooks are imported into the new instance | SCORCH_01 checks completed | 2-2 | Check that the runbook 10.2 is imported and is executing (Path to runbook 10.2)
Check Imported runbooks | Verify that in-scope runbooks are imported into the new instance | SCORCH_01 checks completed | 2-3 | Check that the runbook 20.1 is imported and is executing (Path to runbook 20.1)
Check PDS configuration / data baseline | Verify PDS_Live data is correctly imported | SCORCH_02 checks completed | 3-1 | Check the PDS database contains related mapping table and that the data within the table contains the expected values
Check PDS configuration / data baseline | Verify PDS_Live data is correctly imported | SCORCH_02 checks completed | 3-2 | Check the PDS database contains the table specific to process and that the data within the table contains recent SCOM events
Check PDS configuration / data baseline | Verify PDS_Live data is correctly imported | SCORCH_02 checks completed | 3-3 | Check the PDS database contains the table [dbo].[ACTIVITY_TRACE] and that there are no entries that indicate a problem. NOTE: it is normal for there to be some messages in the table about Alerts that cannot be updated as this is due to alerts that have been groomed from SCOM
Confirm Items are created/updated/assigned | Verify Service Desk Requests pickup alert from PDS |  | 5-1 | Confirm that the runbook 15.1.1_Create_Service Desk_Request picks up an alert from the PDS when it reaches the correct state for ticket creation
Confirm Items are created/updated/assigned | Verify Ticket is created in Service Desk |  | 5-2 | Check that ticket is created
Confirm Items are created/updated/assigned | Verify Ticket fields are mapped correctly, and ticket is assigned correctly |  | 5-3 | Confirm field mapping and ticket assignment is correct in ticket
Confirm Items are created/updated/assigned | Verify Ticket number is correctly recorded in the PDS |  | 5-4 | Confirm Ticket Number is correctly recorded in the PDS
Updated (Resolved) tickets | Confirm Ticket was closed in Service Desk |  | 6-1 | Close a Ticket in Service Desk that was created
Updated (Resolved) tickets | Confirm Monitor detects ticket closure |  | 6-2 | Confirm that runbook 20.1.1_Monitor_Service Desk_Resolved is detects the closure
Other | Check Error Handling |  | 7-1 | Check Error Handling

## Glossary
Tab | Title | Description
General | Company | Company Name
General | Test Team Lead | Name of person leading the testing
General | Test Team Members | Names of people involved with the testing broken out by function or area of expertise
General | Test Start Date | Date testing begins
General | Test End Date | Date testing ends
General | URL | URL of
General | Browser | Browser used during testing
General | Test Summary | Each Category Status (Red = Failed, Amber = In Process, Green = Passed)
Test Activity Control Log | Test Summary | Summary/Description of the test Category/Section/Chapter/Phase performed
Test Activity Control Log | Success | Was the test a success
Test Activity Control Log | Completed By | Person signing off on success/failure of the test
Test Activity Control Log | Date | Date this test or phase was completed
Test Activity Control Log | Result | Comments about Results
Test Activity Control Log | Next Step | Next step to be performed
Test Plan Detail | Category | Category/Section/Chapter/Phase of the Test Plan
Test Plan Detail | Task | Task or function being tested
Test Plan Detail | Pre-Condition | Any pre-requisite task in this test plan that must be tested successfully before attempting this task
Test Plan Detail | Step # | Unique reference for a step in the test plan
Test Plan Detail | Step Description | Detailed information about the step in the test plan to be completed at this time
Test Plan Detail | Expected Result | Expected result of the step to be completed at this time
Test Plan Detail | Actual Result | Detailed information/text from the result - detailed observavtion.
Test Plan Detail | Pass (True/False) | Did this step produce the expected result?
Test Plan Detail | Defect # | Unique reference number for an issue that occurred during testing.
Test Plan Detail | Comments/Clarifications | Details, notes, or additional useful information about this step